Scoring Notes
3-8 ELA & Math 2012

Scheduling of Dates

- One grade/per day vs multiple grades/day

  - Need additional support for multiple grades/day

- Overlap of scoring and test administration days

- Scheduling adj. grades on back-to-back days (ex. 7, 8)

- Plan for “closed” day

Scheduling Hours

- Some tests (ELA)  1 day to score – was rushed

- Time for ELA

- People leaving

  - Hours stuff?

  - Contractual

  - Address in advance

  - Having enough scorers

- Pressure to limit practice, training – get it done, pressure to finish

- Clarity & repeat comm of hours

Scheduling Scorers

- Prename fac is needed

- Scorers traveled

  - Bank of scorers – from retirees

  - Scoring overlap with adm of other test

- HS (& other upper level) teachers scoring tests

- People leaving before scoring was an issue (esp. coaches)

- Scorers felt pressure to finish

- Subs for scorers who were absent

- Communication from planning committee →district →scorers

- Number of scorers required →how to supply qualified teaches (eg. Math)

Roles (BOCES, district, clerical)

- Good organization

- Smooth operation

- Clear identification of roles & responsibilities

- Sufficient clerical support

- Written out step-by-step clerical process

- Clerical support →trained, experienced – clear process

- 2 pt of contact for clerical

- Some sites – clerical was down – others were getting in/out

- Scoring leaders, if co-training, should meet/work ahead of time

- Amount of time spent preparing by scoring leaders

- Need training/process for table facilitators

Daily Mechanics of Scoring

- Randomization of scorers vs. randomization of papers

- Spirit of regs →randomization

- Process of making sure papers are scored by ≥ 3 scorers

  - Split the room →separate Qs

  - Distribute & collect papers x4

  - Score separate Qs at table

- Need additional time for training, practice, CAS

Daily Mechanics of Handling

- Very specific protocol for handling

- Sufficient clerical support

- One point of contact/manager of the process

- If papers are randomized → will need additional support

RIC

- Communication glitch – who should be called to correct errors/supply missing info? (vested interest)

Other

- Snow day!

- Interpreters/translators for test administration?

- Size of sites – what is optimal?

- Concern about # of errors during testing/scoring

- Support from Pearson – inter-site reliability